## Read Me
Product Backlog — Verity Platform Demo/Review Meeting
Source: Uploaded meeting transcript (auto-generated, single-speaker diarization label).
Important note on speaker attribution: the transcript labels every line with one speaker
name regardless of who was actually talking, so individual quotes could not be reliably
attributed to a specific person. 'Mentioned By' is marked Unknown throughout for this reason.
No timestamps were present in the source transcript, so 'Transcript Timestamp' is Unknown throughout.
Tabs in this workbook:
Main Backlog — every actionable item, one row each, with full detail.
Bugs Summary, Improvements Summary, New Features, UI-UX Suggestions, Technical Tasks,
Documentation Tasks, Research Tasks, Open Questions, Decisions Made, Duplicate Requests
— filtered views derived from the Main Backlog tab.

## Main Backlog
ID | Title | Type | Priority | Status | Page / Module | URL / Route | Component | Platform | Description | Current Problem | Suggested Improvement | Expected Result | Acceptance Criteria | Dependencies | Mentioned By | Transcript Timestamp | Transcript Evidence | Frequency | Confidence | Notes
TASK-001 | Post-verification redirect points to localhost instead of production URL | Bug | Critical | To Do | Sign Up / Email Verification | /verify | Auth / Email Verification Link | Web | After signing up, the verification email link redirects to a localhost URL instead of the hosted app URL, so the link cannot be opened. | Environment variable for the site URL is still set to a localhost address (with port), so verification links are broken for anyone outside the dev machine. | Update the environment variable used to build verification links so it points to the production/staging URL (app.verity.ph) instead of localhost. | Verification emails contain a working link that goes directly to the live app. | Clicking the verification link in the email signs the user in / verifies them without manual URL editing. | Environment variable configuration, email templating service | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Tried to sign in and it sent the verification to my email, but when I tried to verify it redirected me to a site that can't be reached... Oh, it's a localhost. | 2 | High | Recurred again during the talent invite-acceptance flow; same root cause. User had to manually edit the URL (replace localhost:port with app.verity.ph) to proceed.
TASK-002 | Password reset email intermittently not delivered | Bug | High | To Do | Auth / Password Reset | Unknown | Forgot Password Flow | Web | Requesting a password reset email worked the first time but failed to arrive on a subsequent attempt. | Reset email was not received on the second/later request, blocking the user from resetting their password. | Investigate email delivery reliability for password reset (rate limiting, provider queue, spam filtering) and add retry/resend logic. | Every password reset request reliably delivers an email within a short, consistent time window. | Requesting a reset link always results in an email delivered (or a clear error if it fails). | Email provider integration | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | It worked earlier, but I guess the second time... the reset password email did not go through. | 1 | Medium | Unknown
TASK-003 | Plus-addressing (email alias) test accounts cause password-reset confusion | UX Improvement | Medium | To Do | Auth / Password Reset, Onboarding | Unknown | Login / Password Reset Form | Web | Team uses email plus-aliasing (e.g. name+role@gmail.com) to test multiple roles with one inbox, but users forget to include the alias when resetting password, causing 'invalid password' errors tied to the wrong account. | No guidance in the UI reminding users which exact email (including the +alias) to use for reset/login when using aliased test accounts. | Add onboarding documentation/tooltip explaining plus-addressing for internal testers, and/or show which email address a reset link was sent to. | Testers can reliably reset passwords for aliased test accounts without confusion. | A user resetting a password for an aliased account is not blocked by mismatched email entry. | Documentation, onboarding guide | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Because if I... the forgot password would of course go to my original email and not the plus VA because I don't have this email originally... this is confusing for me. | 3 | Medium | Internal testing convention, not necessarily a public-facing bug; documentation for team may be the real deliverable.
TASK-004 | Signup 'invalid password' error gives no explanation of requirements | Bug | High | To Do | Sign Up | Unknown | Sign Up Form / Password Field | Web | When account creation fails due to password validation, the form does not explain why (no rules, no field-level error). | User could not tell what made the password invalid and had to guess (eventually adding a number). | Show inline validation messaging with the specific password requirements and which ones are unmet. | Users understand exactly why a password was rejected and how to fix it. | An invalid password attempt shows a specific, actionable error message next to the field. | Shared password validation logic across signup/invite/reset flows (see related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | When we get an error like this, we need to display why it failed... let me just put the number one, and that should solve that hopefully. | 1 | High | Unknown
TASK-005 | Password validation rules inconsistent across signup, invite-accept, and reset flows | Bug | High | To Do | Auth (Sign Up, Accept Invite, Password Reset) | Unknown | Password Field / Validation | Backend | The password reset and invite-registration flows did not enforce the same password rule (e.g. requiring a number) that the signup flow enforced. | Password validation logic is duplicated/inconsistent, so a password valid in one flow can be rejected in another. | Centralize password validation into a single shared rule set/function used by all three flows. | The same password policy is enforced identically everywhere a password is set or changed. | Attempting the same password string produces the same accept/reject result in signup, invite, and reset. | Shared validation utility/backend function | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | It's interesting also because the password reset didn't require this either, or the registration from the invite didn't require this also, so they need to use the same tests to make sure the password is proper. | 1 | High | Unknown
TASK-006 | API errors are not surfaced to the user with useful detail | Improvement | High | To Do | Global / Error Handling | Unknown | Error/Toast Component | Frontend | Failed requests do not show the user why they failed; decision was made on how much detail to expose based on HTTP status. | Users see no explanation (or a generic failure) regardless of whether the error was a validation problem (400) or a server problem (500). | For 4xx errors, display the specific validation message returned by the API. For 5xx errors, show a generic 'something went wrong on our end' message (do not expose server internals). | Users get actionable feedback on their own mistakes, without leaking backend errors on server failures. | A 400 response renders the specific field/reason; a 500 response renders a generic safe message. | Backend error response structure/standardization | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | So it's a 400... we can display why it failed. 500 we shouldn't, because it's a server error... we should say something happened on the server or whatever. | 1 | High | Unknown
TASK-007 | No onboarding/instructions after accepting a Talent (VA) invite | Feature | High | To Do | Talent Portal / Onboarding | Unknown | Onboarding Flow | Web | A newly invited Talent/VA user lands directly on the profile form with no guidance on what to do or why. | New users are confused about next steps immediately after accepting an invite. | Add an onboarding sequence/instructions shown right after a new invite is accepted, explaining the required setup steps. | New VAs understand what to fill out and why before they start. | First login after invite acceptance shows onboarding guidance before/alongside the profile form. | Profile form, Rules of Conduct acknowledgment (related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | So they might need to be some sort of onboarding that we do for a new invite, or maybe some instructions on getting set up. | 1 | Medium | Unknown
TASK-008 | Yes/No profile fields should be toggle switches, not free text | UI Improvement | Medium | To Do | Talent Profile Form | Unknown | Form Field (Yes/No questions) | Web | Certain profile questions expecting a yes/no answer are implemented as text entry instead of a toggle/checkbox. | Users must type 'yes' or 'no' manually, which is error-prone and inconsistent. | Convert yes/no questions into a toggle or checkbox component. | All boolean profile questions are answered via a single tap/click toggle. | Every yes/no field in the profile form renders as a toggle, not a text box. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | This could be a toggle box. Same over here. | 2 | Medium | Mentioned for at least two separate yes/no fields (e.g., backup connection/equipment questions).
TASK-009 | Profile form loses entered data if user clicks away without explicit save | Bug | High | To Do | Talent Profile Form | Unknown | Form / Field Blur Behavior | Web | Clicking outside a field (losing focus) does not persist the value automatically. | Users could lose entered information if they click elsewhere before manually saving. | Autosave field values on blur, or persist all in-progress form data locally until final submit. | No data entered in the profile form is lost due to navigating away or clicking another field. | Filling a field, clicking elsewhere, and reloading/returning shows the previously entered value retained. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | If I click off, it needs to save, or at least have me not lose my information. Otherwise I have to save each time. | 1 | High | Unknown
TASK-010 | Skills/Tools fields need multi-select or autocomplete instead of free typing | Improvement | Medium | To Do | Talent Profile Form | Unknown | Skills / Tools Input Field | Web | Skills and tools are entered as manually typed, comma-delimited text rather than selected from a list. | Manual typing is inconsistent (formatting, spelling) and harder to search/filter on later. | Upgrade the field to support typing plus selecting from a suggested/existing list (autocomplete with add-new capability), similar to the experience-level and tags fields. | Users can quickly add standardized skills/tools via suggestions while still being able to add new ones. | Typing in the field surfaces matching existing entries; selecting one adds it as a tag; new terms can still be added. | Tag/keyword data model for skills and tools | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | So this one you have to type manually... we could upgrade it so that we either type manually or start typing and then select one. | 1 | Medium | Unknown
TASK-011 | Clarify delimiter/UX pattern for multi-value list fields (comma vs. add button) | Question | Low | To Do | Talent Profile Form | Unknown | Multi-value Input Fields | Web | Team was unsure whether list-style fields (skills, tools, languages) should be comma-delimited text or use a '+' add button per entry. | Inconsistent input pattern across similar fields could confuse users. | Decide on and standardize one interaction pattern for all multi-value fields. | All multi-value fields behave the same way. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Should this be comma delimited, or if we enter it in we had a plus button and it adds it or something. | 1 | Low | Left open in the meeting; no final decision recorded.
TASK-012 | Remove 'Internet Provider' field; keep upload/download speed test fields | Decision | Low | To Do | Talent Profile Form | Unknown | Internet/Equipment Section | Web | Team decided the ISP name itself is not useful information for (overseas) clients, but connection speed is. | Form currently asks for internet provider, which clients would not recognize/care about. | Remove or de-prioritize the internet provider field; keep and possibly require upload/download speed fields (e.g., via speed test upload). | Client-relevant connectivity info (speed, backup connection) is retained; irrelevant provider-name field is dropped. | Form no longer requires the ISP name field. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Internet provider not needed, but the upload speed and the download speed... the usual thing that the client would ask. | 1 | Medium | Unknown
TASK-013 | Convert Computer/OS field into a dropdown with Windows/Mac/Linux options | Improvement | Low | To Do | Talent Profile Form | Unknown | Equipment Section - Computer/OS Field | Web | Some clients care about a VA's operating system (e.g., requiring Windows); currently there's no structured way to capture this. | OS/computer type is not captured in a structured, filterable way. | Add a dropdown (single or multi-select) for OS: Windows / Mac / Linux. | OS availability can be filtered/searched for client matching. | Profile form includes a Windows/Mac/Linux selector for the VA's computer(s). | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | There are some clients that are, you know, particular... if they only want Windows or something, so maybe you can keep that one... we can make that three or a drop down for the three to be selected. | 1 | Medium | Unknown
TASK-014 | Profile form fields should all be optional to allow partial save | Improvement | High | To Do | Talent Profile Form | Unknown | Form Validation | Web | Some fields are currently required, blocking the user from saving/progressing until filled. | User could not save the form because required fields were empty, forcing them to leave data blank/fake just to proceed. | Make all (or most) profile fields optional so partial profiles can be saved and completed later. | Users can save incomplete profiles and finish them later without being blocked. | Submitting the form with empty optional fields succeeds without validation errors. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | All of these shouldn't be required. I think this should all just be optional, otherwise I can't even save this. | 1 | High | Unknown
TASK-015 | Clarify and document the 'freeze on submit' behavior for locked profile sections | Documentation | Medium | To Do | Talent Profile Form | Unknown | Position Details / Locked Fields | Web | Certain fields (e.g., position details: why joined Verity, strengths, growth areas) become uneditable ('frozen') once submitted; this behavior confused testers. | Users don't understand why a section becomes locked after submission, and there's no way to edit afterward. | Keep the freeze behavior (agreed as intentional to preserve original answers) but explain it clearly during onboarding, and consider still displaying the response even if not editable. | Users understand upfront that these answers are locked after submission and won't be surprised. | Onboarding copy or a UI note explains the freeze behavior before the user submits. | Onboarding flow (related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | So you can edit it once you submit it?... Yeah, cuz once I lock it I won't... have the ability to edit... but that should be more of an onboarding thing. | 1 | Medium | Unknown
TASK-016 | Block access to other app sections until required profile section is complete | Feature | Medium | To Do | Talent Portal | Unknown | Navigation / Route Guards | Web | Users can currently navigate to other screens before completing the core profile/position-details section. | A VA could skip the mandatory profile section and browse other areas of the app. | Add a route guard that keeps a user on the required onboarding/profile section until it is completed. | VAs cannot access other app screens until the mandatory profile fields are filled and submitted. | Attempting to navigate away before completion redirects back to the incomplete section. | Profile form completion state (backend flag) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | I think they shouldn't even be able to get to these other screens without having to fill out this first. | 1 | Medium | Unknown
TASK-017 | Add file type/size and duration limits for intro video upload | Feature | Medium | To Do | Talent Profile Form | Unknown | Intro Video Upload | Web | There is currently no stated restriction on file size/duration for the required intro video. | Unrestricted uploads could be very large or too long, and there's no guidance for VAs on expected length. | Add upload size/type limits and a required speaking length (e.g., 30-60 seconds) with a prompt like 'tell us about yourself in 60 seconds'. | Intro videos are consistently short, appropriately sized, and easy to review. | Upload rejects videos exceeding size/duration limits and shows the requirement to the user. | Video storage/CDN | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Is there a size restriction to the upload?... how about like, would that affect... we require the VA to speak like less than 30-60 seconds. | 1 | Medium | Unknown
TASK-018 | Allow recording the intro video directly on the Verity site | Feature | Low | To Do | Talent Profile Form | Unknown | Intro Video Upload | Web | Currently VAs must create and upload a video file themselves rather than record in-app. | Recording elsewhere and uploading is extra friction for the VA. | Integrate an in-browser recording feature so VAs can record their intro video directly on the platform. | VAs can record and submit an intro video without leaving the site. | A 'record now' option is available next to the upload option on the intro video step. | Media capture/integration, storage | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | That's an integration I can look into also, where we can record that directly on the Verity site itself, rather than having them figure out what to do or where. | 1 | Low | Unknown
TASK-019 | Government ID upload feels intrusive to some VAs (needs review) | Question | Medium | To Do | Talent Profile Form | Unknown | Documents Section - Government ID | Web | A tester flagged that requiring a government ID upload feels intrusive; no resolution was reached. | Requiring government ID may reduce sign-up completion or feel invasive without clear justification shown to the user. | Consider explaining why the ID is required (verification/compliance) or evaluate whether it's strictly necessary at this stage. | VAs understand why ID verification is requested, improving trust and completion rates. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Yeah, the government ID kind of feels intrusive. I understand. | 1 | Low | No resolution reached in the meeting; flagged as open concern.
TASK-020 | Move Workspace Photo out of Documents dropdown into Personal/Contact section | Improvement | Medium | To Do | Talent Profile Form | Unknown | Documents Section / Personal Info Section | Web | The workspace photo is currently grouped under general document uploads rather than with personal/profile info. | Workspace photo is buried in a generic documents dropdown instead of being prominent, client-facing profile info. | Move workspace photo upload to the Personal and Contact info section, and require it as part of onboarding. | Workspace photo is easy to find, required at onboarding, and visible with other profile essentials. | Workspace photo field appears in Personal/Contact section, not under Documents. | Onboarding requirement flag | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | We should probably put it somewhere else, like extract it from the drop down... and also require it as part of their onboarding. | 1 | Medium | Unknown
TASK-021 | Add a required profile headshot photo visible to clients | Feature | Medium | To Do | Talent Profile Form | Unknown | Personal Info Section | Web | There's a photo upload for workspace, but a personal headshot photo (visible on the client-facing profile) was called out as a good addition. | No dedicated headshot photo field currently shown on the profile. | Add a headshot photo upload field, shown to clients viewing the VA's profile. | Clients see a professional photo when viewing a VA profile. | Profile includes a photo field distinct from the workspace photo, displayed on the client-facing profile view. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Of course, a photo of the VA... Photo upload. Okay, that's a good call. | 1 | Medium | Unknown
TASK-022 | Add 'About Verity' (mission/vision) content to the Talent portal | Feature | Low | To Do | Talent Portal | Unknown | Static Content / About Section | Web | Reviewing the Talent side, the team felt company mission/vision info about Verity was missing. | New VAs have no in-app place to read about Verity's mission and vision. | Add an 'About Verity' section including mission/vision statements. | VAs can read about the company within the app. | An About/Company section exists within the Talent portal. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | All about Verity, like the mission vision, I think we need to put that also here. | 1 | Low | Unknown
TASK-023 | Build native time-tracking app with screenshots and activity monitoring | Feature | High | To Do | Time Tracker | Unknown | Time Tracking App (Desktop) | Desktop | Currently only a manual time-entry web view exists; the team plans a proprietary downloadable time tracker similar to TimeDoctor/Upwork with screenshots and activity monitoring. | Web-based time tracking only supports manual entries, offering no automated proof-of-work for clients. | Build and ship an installable desktop time-tracking app with automatic time capture, periodic screenshots, and activity logging. | Clients and VAs both get automatic, verifiable time-tracking data comparable to third-party tools. | VAs can install a desktop tracker that logs time, takes screenshots, and syncs to their Verity account. | Reuses architecture from an existing internal desktop-conversion app the developer already built | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | The time tracker will be installed on the machine itself... I have the ability to actually write out our own time tracker similar to what TimeDoctor does or Upwork does. | 1 | High | Large, multi-sprint feature; developer noted she already has a working desktop-app conversion pattern to build from.
TASK-024 | Add AI-based detection of mouse-jiggler / suspicious activity in time tracker | Feature | Low | To Do | Time Tracker | Unknown | Time Tracking App - Activity Detection | Backend | Team discussed flagging suspicious activity patterns (e.g., mouse jiggler use) using AI analysis of tracked activity. | No automated fraud/idle-detection exists yet. | Add AI-driven analysis to flag anomalous patterns such as mouse-jiggler usage or repeated idle-like activity. | Suspicious time-tracking activity is automatically flagged for review. | System can flag a tracked session showing mouse-jiggler-like patterns for admin review. | Time tracker feature (above), AI/analytics pipeline | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | We could even run it through AI to detect the mouse jigglers and stuff like that. | 1 | Low | Future enhancement, depends on the core time tracker being built first.
TASK-025 | Add mandatory 'Rules of Conduct' acknowledgment during onboarding | Feature | High | To Do | Onboarding (Talent) | Unknown | Onboarding Flow - Agreement Step | Web | Team wants a rules-of-conduct step (e.g., no poaching/'stealing' clients) that VAs must read and acknowledge before using the platform. | No formal rules-of-conduct acknowledgment currently exists in onboarding. | Add a required rules-of-conduct / code-of-conduct step with explicit VA acknowledgment, completed before other features unlock. | All VAs have explicitly agreed to conduct rules (e.g., not soliciting clients outside the platform) before starting work. | A VA cannot proceed past onboarding without checking/acknowledging the rules-of-conduct step. | Onboarding flow, access-gating (related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | We're missing the onboarding... rules of conduct or something... we need to introduce and they need to acknowledge that... no stealing our clients. | 1 | High | Unknown
TASK-026 | Add a 'Projects' section to the Talent (VA) portal | Feature | Medium | To Do | Talent Portal | Unknown | Projects / Contracts Section | Web | VAs need visibility into what they are actively working on beyond just Clients/Contracts lists. | There is no clear place for a VA to see current project/task details. | Add a Projects section for VAs, showing assigned project(s), tasks, and status. | VAs can see what project(s) they're working on and its current status. | A logged-in VA with an active assignment can view the project's details from their portal. | Client/contract-to-VA assignment feature (see Admin section items) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | There's some things that could be added such as projects... the VA needs to know what they're working on. | 1 | Medium | Unknown
TASK-027 | Restrict VA-client communication to the in-platform chat system only | Decision | Medium | To Do | Talent Portal / Client Communication | Unknown | Chat System | Web | Team decided VAs should communicate with their assigned client only through the platform's built-in chat, not other channels. | Unknown | Enforce that VA-to-client communication occurs only via the platform chat (no external channels for this relationship). | All VA-client conversations are captured centrally in Verity for oversight/record-keeping. | No alternate channel is provided/suggested for VA-client contact within the product. | Chat/messaging system | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | The VA also needs to be able to communicate with their client, the chat system, and only the chat system. | 1 | Medium | Unknown
TASK-028 | Client dashboard should show project status even while pending admin approval | Bug | High | To Do | Client Dashboard | Unknown | Project Request / Status Display | Web | After a client submits a new project request, no corresponding pending project entry appears for them; the request only surfaces as a message/inbox item on the admin side. | Clients cannot see that their submitted project request exists or its pending status. | Show the submitted project request under the client's project list with a 'Pending' status until an admin/account manager processes it. | Clients always see their submitted request and its current status. | After submitting a request, the client's project list shows an entry marked Pending. | Admin project-request/triage endpoint (related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | If that's a thing that's happening then... we need to see the project still, even if it's pending. | 1 | High | Unknown
TASK-029 | Client dashboard needs an explanation of what an 'Account Manager' is | Feature | Medium | To Do | Client Dashboard | Unknown | Onboarding / Info Panel | Web | First-time clients see references to an 'account manager' with no context on what that role means or who it is. | New clients don't understand the 'account manager' concept when it's first referenced (e.g., after submitting a project). | Add a first-login overview/tooltip explaining the account manager concept as their point of contact. | New clients understand who their account manager is and what that role does. | First login for a client shows a brief explanation of the account manager role. | Account Manager assignment feature (related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | We need to have some sort of overview when the client first logs in, so they understand what an account manager is. | 1 | Medium | Unknown
TASK-030 | Show the actual Account Manager's name instead of a generic label | Improvement | Medium | To Do | Client Dashboard | Unknown | Account Manager Reference / Escalation Banner | Web | System references 'the account manager' generically rather than naming the specific assigned person. | Clients can't tell who specifically is handling their account/escalation. | Display the actual assigned account manager's name wherever the role is referenced (e.g., 'Your account manager is Marianne'). | Clients always see the specific person's name tied to their account, not a generic label. | Escalation/project banners display a named account manager, not just the word 'account manager.' | Account Manager assignment feature | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | If this can be referencing the account manager, we should probably say 'your account manager is' something like that. | 1 | Medium | Confirmed by a later message: 'This has been escalated to [Marianne], your Account Manager' already partially exists.
TASK-031 | Build ability to assign an Account Manager to a client | Feature | Critical | To Do | Admin | Unknown | Client Record / Account Manager Field | Web | There is currently no way for an admin to assign a specific account manager (point of contact) to a client. | Project requests and escalations reference an account manager, but no assignment mechanism exists yet. | Add an admin-facing field/workflow to assign (and reassign) an account manager per client. | Every client has a designated account manager on record that can be viewed and changed by admins. | Admin can select an account manager for a client record, and that value is what's displayed to the client. | Client record / user roles | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Do we have a way of assigning an account manager yet?... that needs to be integrated. I'll take note of that. | 1 | Critical | Called out by the team as a concrete missing feature to implement next.
TASK-032 | Design auto-assignment logic for Account Manager based on workload rotation | Research | Low | To Do | Admin | Unknown | Account Manager Assignment Logic | Backend | Team discussed ideas for automatically distributing account-manager assignments (e.g., least number of accounts, role-based eligibility, or simple rotation). | No defined rule yet for how new clients get matched to an account manager. | Research and define an assignment algorithm/rotation and an 'eligible for account manager' role flag. | New clients are automatically or semi-automatically routed to an appropriate account manager. | Unknown | Account Manager assignment feature (above) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | We could pick to see like who has the least amount of accounts under their name... let's get someone in the rotation, the four of us in rotation for the account managers. | 1 | Low | Decided to start with a simple rotation among the four current team members for now.
TASK-033 | Differentiate 'Message' vs 'Project' as distinct structured conversation types | Improvement | High | To Do | Messaging / Communication | Unknown | Chat / Messaging System | Backend | Submitting a project request currently creates a generic chat thread indistinguishable from a normal message. | Project requests and plain messages are structurally the same, making it hard to track/triage them differently. | Introduce a message 'type' (e.g., Message vs. Project) so projects can be handled/triaged with their own structure and status. | Project-related communications are clearly distinguishable from general messages, both in data and UI. | A submitted project appears as a distinctly-typed item, separate from the general message inbox. | Pending project status feature (related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | We should probably delineate like the different types and messages... if it's a project I prefer project to be on its own structure. | 1 | High | Unknown
TASK-034 | Move the 'Message' button to a persistent floating button (bottom-right) on every page | UI Improvement | Medium | To Do | Global Navigation | Unknown | Message Button | Web | The message/contact-account-manager button currently sits in the header rather than as a persistent floating action button. | Placement in the header is less discoverable/consistent than a floating button pattern. | Move the message button to a floating bottom-right position, present on all pages. | Users can access messaging from a consistent, always-visible location on every page. | The message button appears bottom-right on all pages, replacing the header placement. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | This message button could go down on the bottom right instead of on the header. | 2 | Medium | Mentioned twice, including for the client view specifically.
TASK-035 | Add a visual badge/indicator distinguishing which chat is with a client vs. internal | UI Improvement | Medium | To Do | Messaging / Communication | Unknown | Chat Thread Header / Badge | Web | Internal team messaging and client-facing messaging are visually similar, risking someone sending an internal remark to the client by mistake. | No clear visual distinction between an internal conversation and a client conversation. | Add a colored badge/label (e.g., red 'Client') on conversations involving a client. | Team members can immediately tell if a thread is with a client before sending a message. | A conversation with a client displays a distinct badge/label not shown on internal threads. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | If anyone's making like snarky remarks against our clients, they don't accidentally send it to the client themselves. | 1 | High | Unknown
TASK-036 | Fix broken toggle switch styling on Finance/Billing page | Bug | Medium | To Do | Finance / Billing (Client) | Unknown | Toggle Switch Component | Web | A toggle control on the billing page renders incorrectly, appearing to fall off/overflow its container. | The toggle switch UI element is visually broken on the finance/billing page. | Fix the CSS/layout of the toggle component so it renders correctly within its container. | The toggle displays correctly and is fully usable. | The toggle renders fully within its bounding container at all screen sizes tested. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | There's the toggle here needs to be fixed... the toggle's kind of falling off the button. | 1 | Medium | Unknown
TASK-037 | Fix scroll/tab rendering artifact on Finance/Billing page tabs | Bug | Low | To Do | Finance / Billing (Client) | Unknown | Tab Navigation Component | Web | There's a visual artifact related to horizontal scrolling of tabs on the billing page; reportedly the only page with this issue. | Tab scrolling shows a rendering glitch/artifact not seen elsewhere in the app. | Fix or remove the problematic scroll behavior/component on this page's tab navigation. | Billing page tabs render cleanly with no visual artifacts while scrolling. | Scrolling the billing page's tab bar shows no visible rendering glitches. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | There's some artifact here for the scrolling for the tabs on the finance page... that's the only page that does that so far. | 1 | Low | Unknown
TASK-038 | Switch client billing cycle from monthly to weekly (paid in advance) | Decision | High | To Do | Finance / Billing | Unknown | Billing Cycle Configuration | Backend | Team debated monthly vs weekly billing; decided weekly (charged every Monday, similar to Upwork) is safer for cash flow and dispute risk while the company is small. | Monthly upfront billing risks losing a full month's revenue if a client disputes/steals time from a VA; a week's exposure is more manageable. | Implement weekly billing cycles (Monday-based) as the default, with the ability for admins to configure different cycles later. | Clients are billed weekly by default, reducing financial exposure from disputes. | New client accounts default to a weekly billing cycle; admin can view billing cycle settings. | Stripe integration, admin billing settings | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | So an Upwork does their bill cycles every Monday... since we have the card, then weekly... for now I think we just keep it week by week. | 1 | High | Admin-configurable billing cycle changes noted as a later enhancement.
TASK-039 | Replace default Stripe-branded 'Add Payment Method' page with custom-branded page | Improvement | Medium | To Do | Finance / Billing | Unknown | Add Payment Method Page | Web | Clicking 'Add Payment Method' currently redirects to a generic Stripe-hosted page with Stripe's own branding/logo. | The payment page breaks the Verity branding experience by showing third-party (Stripe) branding. | Build a custom-branded payment method page using Stripe's underlying APIs/Elements rather than the default hosted redirect. | Adding a payment method feels like a native part of the Verity site with consistent branding. | The Add Payment Method flow shows Verity branding throughout, with no exposed third-party page/logo. | Stripe integration | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | That's something that I need to fix up... the way that I have it built is custom and can handle this sort of thing without like flashing the [third-party] logo and orange and all that stuff... it'll be its own page. | 1 | Medium | Unknown
TASK-040 | Define Account Manager workflow for handling disputed invoices | Feature | Medium | To Do | Finance / Billing | Unknown | Invoice Dispute Flow | Web | Once an invoice is marked disputed, there is currently no further action available in the flow, and no defined process for the account manager to resolve it. | Disputed invoices reach a dead end with no resolution workflow. | Build a dispute-handling workflow so the assigned Account Manager is notified and can resolve/respond to disputes. | Disputed invoices are routed to and resolved by the account manager. | A disputed invoice generates a task/notification for the account manager and supports a resolution action. | Account Manager assignment feature (related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | We need to make sure that the Account Manager handles these disputes... we haven't got to the account manager yet. | 1 | Medium | Unknown
TASK-041 | Require client company info and agreements before granting full platform access | Feature | Medium | To Do | Client Onboarding | Unknown | Onboarding Flow (Client) | Web | Client-side onboarding currently lacks a step for collecting company information and agreement acknowledgments. | No structured onboarding step currently collects required client info/agreements. | Add an onboarding step for the client to provide company info and accept required agreements before proceeding. | All clients have completed company info and agreement acknowledgment before using the platform. | A new client cannot bypass the company-info/agreement onboarding step. | Onboarding flow (Talent onboarding is a related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | [The client should provide] information about themselves; that needs to be a part of the onboarding for the client, along with the agreements. | 1 | Medium | Unknown
TASK-042 | Investigate automated (cron/AI) checks instead of manual-only compliance notifications | Research | Low | To Do | Client Onboarding / Compliance | Unknown | Notification / Compliance System | Backend | Team wondered whether compliance-related checks should be automated (scheduled job) rather than only firing as they happen. | Currently checks appear to be purely event-driven notifications with no scheduled audit. | Evaluate adding a scheduled job (or AI-assisted review) to periodically verify compliance-related items. | Compliance gaps are caught proactively rather than only via one-off notifications. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Do we have a cron job set that checks for these things, or is it just as it happens, it does the notification?... something for the AI to check out later. | 1 | Low | Left as an open idea, no decision made.
TASK-043 | Clarify/rename the Admin 'Team' page (individuals vs. departments) and consider card view | UI Improvement | Low | To Do | Admin - Team | Unknown | Team Page / List View | Web | The 'Team' page label was confusing: it lists individual internal staff members, not departments/teams as the name implies. | 'Team' naming suggests groups/departments, but the page actually shows individual admins/staff members. | Rename the page/section for clarity, and consider a card-based layout (one card per department, e.g. Operations, Recruiters) if a grouped view is also needed. | Users correctly understand whether they're viewing individuals or departments/groups. | Page label and layout clearly communicate that it shows individual people (or, if changed, grouped departments). | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Team to me kind of lets me know that this is a group we're working with, but these are actually individual people... this part's gonna get a little bit tricky. | 1 | Low | Unknown
TASK-044 | Split Admin Users list by role (Admin / Client / Sales / Talent) | Improvement | High | To Do | Admin - Users | Unknown | Users List / Filter | Web | The Users list currently mixes all roles together (admins, clients, sales, talent) with no clean way to view by role. | It's very messy to review users because all roles are mixed in one list. | Add filtering/segmentation of the Users list by role, and a summary of user counts per role for admins. | Admins can quickly view/filter users by their specific role. | The Users list can be filtered to show only Admin, only Client, only Sales, or only Talent users. | User role/permission model | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | It's actually very messy, like all of the users are mixed, like the admin, the client, the sales, and the talent. | 1 | High | Also requested: a view of total user counts per role, and availability/hours info per talent user.
TASK-045 | Prevent accidental role changes when editing a user account | Security | Critical | To Do | Admin - Users | Unknown | Edit User Modal - Role Field | Web | The Edit User screen currently allows changing a user's role (e.g., could accidentally set a client or VA to Admin), which is a serious security risk. | An admin could accidentally grant a client or VA elevated (e.g., Admin) access via the role dropdown while editing other fields. | Lock the role field in the edit-user view (display-only) and disallow role changes entirely through this UI; handle role changes via a separate, deliberate, and restricted process if ever needed. | Role changes cannot happen accidentally; the role is shown but not editable from the standard edit-user screen. | Editing a user account never allows the role value to be changed/saved. | RBAC system (mentioned as a future refinement) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | I think we don't allow changing roles at all... it's very easy to say okay admin, oops, I didn't mean that. Suddenly someone has access to all the internal system. | 1 | Critical | Team also floated (but did not commit to) restricting edits to @[company-domain] admin accounts only; final decision was to disallow role editing outright, to be refined later with RBAC.
TASK-046 | Rename Admin 'Projects' (triage) section for clarity | Improvement | Low | To Do | Admin - Projects | Unknown | Projects List / Page Title | Web | The current 'Projects' label doesn't reflect that this view functions as a triage list of newly submitted, unassigned project requests. | Naming doesn't communicate the section's actual triage purpose. | Rename the section to something like 'Open Projects' to better reflect newly created projects awaiting assignment to a VA. | Admins immediately understand this is where new/unlinked project requests are triaged. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | This projects section here should probably have a name change... I'm thinking like open projects... this could end up as a triage of sorts. | 1 | Low | Unknown
TASK-047 | Build VA directory with filtering and direct-message capability for assignment | Feature | High | To Do | Admin - Projects / Talent | Unknown | VA Directory / Profile View | Web | Admin needs the ability to browse/filter a directory of VAs (profile view) and message a VA directly to notify them of a new assignment. | There is currently no VA directory/profile browsing view with filtering for admins to find and contact a VA about an assignment. | Build a searchable/filterable VA directory (profile cards or list) with a 'message this VA' action for assignment notifications. | Admins can find an appropriate VA and notify them of an assignment directly from the directory. | Admin can filter VAs by criteria and send a message to a selected VA about a new assignment. | Messaging system, VA profile data | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | The ability to like click in and filter out VAs from a directory of some sort... and then the ability for an admin to message that VA directly and then tell them about the assignment. | 1 | High | Unknown
TASK-048 | Build workflow to link/assign a VA to a client's project | Feature | Critical | To Do | Admin - Projects | Unknown | Project-to-VA Assignment | Web | There is currently no visible/working way for an admin to connect a submitted client project to a specific VA. | The ability to connect a VA to a client (project assignment) is not yet visible/functional, partly because project requests aren't flowing through correctly yet. | Build the end-to-end workflow: admin reviews an open project, selects/assigns a VA, and the assignment links project, client, and VA together. | Admins can assign any open project to a specific VA, establishing the client-VA-project relationship. | An admin can select an open project and assign a VA to it, and that assignment is then reflected in both the client's and VA's views. | Client project-request flow, pending-status feature, VA directory (related items) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | The ability to view [the] client's project proposal, that's still broken. And then the ability to connect a VA to a client, that's something I'm not yet seeing. | 1 | Critical | Unknown
TASK-049 | Decide real-time messaging approach: WebSocket/SSE vs. periodic polling | Technical Debt | Medium | To Do | Messaging / Communication | Unknown | Chat System - Sync Mechanism | Backend | Team is unsure whether new messages arrive in real time and discussed a fallback of polling every ~15 seconds if server-sent events aren't implemented. | It's unclear whether messages update live; no explicit refresh strategy has been confirmed. | Confirm/implement either an SSE-based real-time update or a ~15-second polling refresh for new messages. | New messages appear promptly without requiring a manual page refresh. | A new message sent to a user appears in their chat view within the agreed refresh interval without manual reload. | Chat/messaging system | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | I'm not sure if it's real time... we should probably actually do like, if we're not doing the SSE, we should do refresh like every 15 seconds. | 1 | Medium | Unknown
TASK-050 | Scope sales leads to the owning sales rep by default (no cross-rep visibility) | Decision | High | To Do | Sales - Leads / Pipeline | Unknown | Leads List / Filter | Web | Leads are currently shown under an 'All' filter across sales reps; team decided each rep should see only their own leads by default, with admins seeing everyone's. | Sales reps could currently see (and potentially contact) leads that aren't theirs, which raises an ethical/poaching concern. | Default the leads view to the logged-in sales rep's own leads only; restrict cross-rep lead access; admins retain full visibility across all leads. | Sales reps cannot see or contact another rep's leads; admins can see everything. | A sales rep's default leads view shows only leads they own; an admin's view shows all leads regardless of owner. | User roles/permissions | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | It can get very messy if a sales agent contacts someone else's potential client... very unethical... I think we just don't allow it and let salespeople keep track of their own leads. | 1 | High | Unknown
TASK-051 | Add sortable 'Date' column to Leads/Pipeline table | UI Improvement | Low | To Do | Sales - Leads / Pipeline | Unknown | Leads Table | Web | It's unclear whether the notes/leads list is sorted by latest activity or creation date; there's no visible sortable date column. | Users can't easily verify or change the sort order of leads by date. | Add a visible 'Date' (created/updated) column with clickable column-header sorting. | Users can see and control whether leads are sorted by date ascending or descending. | Clicking the Date column header toggles sort order of the leads table. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | We need the ability to see the date, and then also click on the column header to sort by that. | 1 | Low | Unknown
TASK-052 | Merge Kanban/Task board view into the Leads table instead of a separate disconnected view | Improvement | Medium | To Do | Sales - Leads / Pipeline | Unknown | Tasks / Kanban View | Web | A separate 'Tasks' area exists with kanban-like functionality that seems disconnected from the Leads/Pipeline table it should be tied to. | Tasks and Leads currently behave as two disconnected areas even though creating a task routes toward leads. | Add a Kanban-style view option to the Leads table itself (reusing the existing task-board functionality) rather than maintaining a separate Tasks section. | Users manage leads in either table or kanban view from a single unified Leads section. | The Leads page offers a toggle between table view and kanban/board view of the same underlying leads/tasks data. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | This one here needs to be a change... I think that sells it if we just merge the two, so just add a kanban view to the leads table, and all that functionality is already over there anyways. | 1 | Medium | Unknown
TASK-053 | Rename ambiguous 'New' task button to 'Add Lead' | Bug | Low | To Do | Sales - Tasks / Leads | Unknown | New Task/Lead Button | Web | Clicking the current 'New' button (intended to add a task) actually routes into lead-creation, but the button doesn't say that. | Button label doesn't match its actual behavior (creates a lead, not a generic task). | Rename the button to 'Add Lead' (or similar) to match its actual function. | Users understand exactly what the button will do before clicking it. | The button previously labeled ambiguously is relabeled to clearly indicate lead creation. | Kanban/Leads merge (related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | This one here needs to be a change to add leads or add lead, because when you create the task here, it will direct... to [lead creation]. | 1 | Low | Unknown
TASK-054 | Fix unstyled/ugly scrollbar on the Leads/Pipeline view | UI Improvement | Low | To Do | Sales - Leads / Pipeline | Unknown | Scrollbar Styling | Web | The scrollbar in the leads/pipeline area was called out as visually unpolished. | Default browser scrollbar styling looks out of place compared to the rest of the UI. | Apply custom scrollbar styling consistent with the rest of the app's design system. | The scrollbar visually matches the polish of the rest of the interface. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Scroll bar is ugly. | 1 | Low | Unknown
TASK-055 | Design a clearer, more guided workflow for creating a sales proposal/pricing | Improvement | High | To Do | Sales - Proposals | Unknown | Proposal / Pricing Creation Flow | Web | Setting up a proposal or pricing from the current page is not intuitive for a sales rep and may currently require a separate/complex process. | The current path to send a proposal or set pricing is confusing enough that a sales rep 'might give up and make a mess.' | Redesign the proposal/pricing flow to be more guided and intuitive specifically for sales users, potentially based on step-by-step sales user stories. | A sales rep can confidently create and send a proposal with pricing without confusion. | A sales rep can complete a proposal/pricing flow end-to-end without external help, in user testing. | Sales user-story documentation (related item), Spencer's CRM review (related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | It's not very intuitive for setting a proposal or the pricing... otherwise they give up and make a mess. | 1 | High | Unknown
TASK-056 | Introduce a dedicated 'Project Manager' role, separate from Admin | Decision | High | To Do | Roles & Permissions | Unknown | User Role System | Backend | Team decided project management responsibilities (communicating with sales, client, and assigned VA) should be a distinct role from full Admin, with access limited to only projects assigned to that manager. | Currently, project-management-type responsibilities would otherwise require full Admin access, which is broader than necessary. | Create a 'Project Manager' role with permissions scoped to projects/clients/VAs assigned to them (can message sales, client, and their assigned VA); Admin retains full access to everything. | Project managers can do their job (coordinate sales, client, VA) without holding full admin rights. | A Project Manager account can access and message only the client/sales/VA tied to their assigned project(s); an Admin account can access everything. | RBAC/permissions system, VA-to-client assignment feature | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | So do we need another role for project management?... it's basically a project manager can communicate with sales... the client... and the VA that's assigned to them. | 1 | High | Unknown
TASK-057 | Decide VA-client contact channel: allow external channels (e.g., WhatsApp) for sales with note-logging | Decision | Medium | To Do | Sales - Client Communication | Unknown | Communication Policy | Web | Team decided sales reps may continue using external channels like WhatsApp with clients for convenience, but should log notes on the lead record, while in-platform messaging remains available as an option. | Unknown | Allow sales reps to use external messaging tools with clients, but require them to copy key details into the lead's notes; keep in-platform messaging available as an alternative, not a requirement. | Sales communication history is still captured for the record, even when done via outside channels. | A lead record supports adding a free-text note capturing an external conversation summary. | Leads/notes data model | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | If the sales prefer to use WhatsApp with the client, that would be easier... I think we've still given the ability to reach out within the platform, just as an option. | 1 | Medium | Confirmed the 'add quick note' functionality already exists for this purpose.
TASK-058 | Confirm document/knowledge-base folder categories are already dynamic (not hardcoded) | Documentation | Low | To Do | Documents / Knowledge Base | Unknown | Folder / Category Structure | Web | Team initially questioned whether category folders (e.g., Services) were hardcoded, then confirmed the folder/subfolder structure is already fully dynamic. | Unknown | No change needed; document that folder categories are dynamic (create group/subfolder/note as needed) for team awareness. | Team has shared understanding that folder structure is user-configurable, not fixed. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | I'm thinking that you actually — these aren't hard-coded at all, they're all dynamic. So that's just me not paying attention. | 1 | Low | No action item; included for completeness since it was raised as a question then resolved live.
TASK-059 | Add optional 'Sales Card' bio/profile page for digital business cards | Feature | Low | To Do | Sales - Profile | Unknown | Sales Rep Bio / Card Page | Web | Idea floated for sales reps to have a shareable bio page (photo + short bio) usable like a digital business card. | No such shareable bio/card feature currently exists for sales reps. | Add an optional profile 'card' page per sales rep with photo and short bio, shareable via link. | Sales reps can share a simple bio link with prospects as a digital business card. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | We could have a sales card or something, like if they upload a photo and put a little bio about them... but that's probably extra. | 1 | Low | Explicitly flagged by the team as a 'nice to have' / lower priority idea.
TASK-060 | Add default email signature template for sales reps | Feature | Low | To Do | Sales - Settings | Unknown | Email Signature Settings | Web | Team liked the existing email signature field and suggested adding a default template. | There is no default/starter template for the email signature field. | Provide a default email signature template that sales reps can customize. | Sales reps start with a professional default signature rather than a blank field. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | I see the email signature, I like that. We should probably have a default [template]. | 1 | Low | Unknown
TASK-061 | Remove/repurpose 'New Lead Assigned' notification given self-managed leads model | Improvement | Low | To Do | Sales - Notifications | Unknown | Notification Settings | Web | Since leads will be self-managed by each sales rep (not assigned by someone else), the 'New Lead Assigned' notification may no longer apply. | A notification exists for a lead-assignment workflow that the team decided isn't how leads will actually work. | Remove or repurpose the 'New Lead Assigned' notification since leads are self-sourced/self-managed rather than assigned. | Notification settings match the actual self-managed leads workflow. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | New lead assigned... again, I think they'll be owning their own leads, so anything that... might be assigning them leads... it's probably not a thing anymore. | 1 | Low | Unknown
TASK-062 | Keep 'Follow-up due' reminder and 'Monday summary' notification features as-is | Decision | Low | To Do | Sales - Notifications | Unknown | Notification Settings | Web | Team reviewed existing notification ideas and explicitly approved keeping follow-up reminders and a Monday summary digest. | Unknown | No changes needed; retain these notification features as currently planned/built. | Sales reps continue to receive follow-up reminders and a weekly Monday summary. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | The follow-up due is probably important to have... and a Monday summary — yeah, I like that too, that's really good. | 1 | Low | Positive decision/confirmation, not a bug or new feature.
TASK-063 | Keep sales goals/targets tracker feature as-is | Decision | Low | To Do | Sales - Goals | Unknown | Goals / Targets Settings | Web | Team approved the existing goals/targets feature (e.g., number of clients or hours) for motivating and tracking sales reps. | Unknown | No changes needed; retain the goals/targets feature. | Sales reps can set and track personal goals/targets within the platform. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | I like these goals... the targets in defaults for the sales... allows them to track quickly whether they're meeting their goal. | 1 | Low | Positive decision/confirmation.
TASK-064 | Add a site-wide Feedback button/section | Feature | Medium | To Do | Global | Unknown | Feedback Widget | Web | Team agreed that having a quick feedback capture mechanism throughout the app would help gather direct user input rather than guessing what users want. | There is currently no dedicated feedback mechanism across the app. | Add a persistent feedback button/section (e.g., near the existing '+' button) so users can submit feedback from anywhere in the app. | The team can quickly collect direct user feedback instead of relying on guesses. | A feedback entry point is available and functional from any page in the app. | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Feedback button, I implement those pretty quickly in the site because that's users telling us what they want, versus us guessing what they want. | 1 | Medium | Unknown
TASK-065 | Publish a changelog with each production deploy | Documentation | Medium | To Do | Process / Release Management | Unknown | Deployment Process | Backend | Team agreed that each deploy should be accompanied by a changelog describing what changed, so testers know what to review. | Currently there's no formal changelog process tied to deploys, making it harder to know what to test after a release. | Establish a lightweight release process: after each deploy, publish a changelog message (in the team's chat/tool) summarizing what changed. | Team members always know what changed and what to test after each release. | Every production deploy is accompanied by a changelog entry visible to the team. | Deployment pipeline | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Each time you make a release, you can ping us on... what you changed... since I'll be deploying it, I can also update a changelog. | 1 | Medium | Unknown
TASK-066 | Set up a booking/calendar link for the (future) point-of-contact/account manager role | Follow-up | Low | To Do | Process / Future Work | Unknown | Booking Calendar | Unknown | One team member noted a personal action item to set up a booking calendar so salespeople can schedule time with them directly. | No booking calendar currently exists for this purpose. | Set up a booking/calendar tool link for the relevant point of contact. | Salespeople (or others) can self-schedule time with the point of contact without back-and-forth. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Some action items I need to do, like the booking calendar, I need booking calendar set up for myself... that's a future meeting problem. | 1 | Low | Explicitly flagged by the speaker as a future, non-urgent item.
TASK-067 | Investigate AI coding assistant (Claude) slowness during development | Research | Low | To Do | Internal Dev Tooling (not the Verity app) | Unknown | AI Coding Assistant Performance | Unknown | A developer reported the AI coding assistant felt slower than usual, especially compared to how it performs on the landing page project versus the main app. | Perceived slowdown and reduced prompt-understanding quality during coding sessions, possibly due to internet connectivity or heavy multi-project usage. | Recommended: verify model selection (e.g., Sonnet/Opus), reduce the 'thinking' level, and start a fresh session per commit to avoid large accumulated context windows. | Coding assistant responsiveness returns to expected levels. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Check your settings, make sure your model is like Sonnet or Opus, and then keep the thinking level to about two or three dots... keep refreshing... changing sessions each commit you do. | 1 | Low | This concerns the team's own AI coding tool usage, not the Verity product itself.
TASK-068 | Complete sales user-story documentation based on current (not idealized) workflows | Documentation | Medium | To Do | Sales / Process Documentation | Unknown | User Story Documentation | Unknown | A document with sales user stories is in progress; team agreed stories should reflect where the process is today rather than an idealized future state. | Existing draft user stories may not reflect the actual current-state workflow, risking design decisions based on an ideal that doesn't exist yet. | Finish/update the sales user-story document to reflect current, real-world workflows as a baseline for design decisions. | Product decisions for the sales flow are grounded in real current-state user stories. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | I think Marianne is also working on... had worked on a document like that... I think those stories just based on where we're at today rather than ideally. | 1 | Medium | Unknown
TASK-069 | Have Spencer review the Sales/CRM module given his prior CRM-building experience | Follow-up | Low | To Do | Sales / CRM | Unknown | Unknown | Unknown | Team suggested involving a colleague (Spencer) who has built CRM systems multiple times before, to review the sales module and suggest improvements. | Unknown | Have Spencer review the current sales/CRM implementation and provide suggestions or flag anything missing. | Sales/CRM module benefits from additional expert review before further development. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Spencer's probably a good resource to kind of use the sales part of this, since he's built out whole CRM several times over... he can probably take a look and see if... anything missing. | 1 | Low | Unknown
TASK-070 | Each team member to independently step through all app roles for future feedback | Follow-up | Medium | To Do | Process / QA | Unknown | Unknown | Unknown | Team agreed that going forward, each person should independently explore the app as different roles (sales, client, VA, admin) and provide feedback after each release, rather than doing a full live walkthrough each time. | Live, synchronous walkthroughs of every role each meeting is time-consuming and not scalable long-term. | Each team member tests the app independently per role after each deploy and shares feedback/replies on the deploy/changelog message. | Feedback is gathered continuously and asynchronously rather than only during scheduled meetings. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | I'll have to step through the site again on my own time... to see, like, if I was a sales agent... this is what I'm expecting. | 1 | Medium | Established as the ongoing process going forward instead of repeating this style of meeting.
TASK-071 | Clarify distinction between 'Event' and 'Project' concepts in Admin/CRM | Question | Low | To Do | Admin - Engagements/Projects | Unknown | Data Model / Terminology | Backend | Team was unsure of the intended difference between 'event' and 'project' entities seen in the admin CRM area. | Overlapping terminology creates ambiguity about which entity to use for what purpose. | Define and document the distinct purpose of 'Event' vs. 'Project' entities in the data model. | Team and future users clearly understand when to use an Event vs. a Project record. | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | Still kind of confused between what event and project does. That's gonna be a use story from me. | 1 | Low | Unknown
TASK-072 | Define the purpose and structure of the 'Engagements' section | Question | Low | To Do | Admin - Engagements | Unknown | Engagements Module | Backend | Team encountered an 'Engagements' section described as tracking every client relationship in one record, but felt it was too early to evaluate. | No clear current need/workflow defined for the Engagements section yet. | Revisit and define concrete use cases for Engagements once core client/project/VA workflows are stable. | Unknown | Unknown | Unknown | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | What's the engagement here?... every client relationship on one record, who knows what and where and how... I think I'm too early on that. | 1 | Low | Explicitly deferred by the team as premature to evaluate.
TASK-073 | VAs should log their own project milestones/work as a 'proof of work' journal | Decision | Medium | To Do | Talent Portal - Projects | Unknown | Milestones / Work Log | Web | For clients who use their own external project-management tools, the team decided VAs should still independently track milestones/work in Verity as a protective record for all parties. | If a client uses an external tool, there's currently no expectation for the VA to keep an independent record within Verity. | Encourage/require VAs to log milestones and work progress within Verity regardless of any external client tooling, to serve as proof of work. | There is always an independent, Verity-side record of a VA's work and milestones, protecting the VA, company, and client. | Every active engagement has VA-logged milestone/work entries visible in Verity, independent of any external client tools. | Projects section (related item) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable) | Unknown | It'll be up to the VA to keep track of the milestones... kind of like a diary, journal on our side, so that we have like proof of work. | 1 | Medium | Unknown

## Bugs Summary
ID | Bug | Page / Module | Priority | Status
TASK-001 | Post-verification redirect points to localhost instead of production URL | Sign Up / Email Verification | Critical | To Do
TASK-002 | Password reset email intermittently not delivered | Auth / Password Reset | High | To Do
TASK-004 | Signup 'invalid password' error gives no explanation of requirements | Sign Up | High | To Do
TASK-005 | Password validation rules inconsistent across signup, invite-accept, and reset flows | Auth (Sign Up, Accept Invite, Password Reset) | High | To Do
TASK-009 | Profile form loses entered data if user clicks away without explicit save | Talent Profile Form | High | To Do
TASK-028 | Client dashboard should show project status even while pending admin approval | Client Dashboard | High | To Do
TASK-036 | Fix broken toggle switch styling on Finance/Billing page | Finance / Billing (Client) | Medium | To Do
TASK-037 | Fix scroll/tab rendering artifact on Finance/Billing page tabs | Finance / Billing (Client) | Low | To Do
TASK-053 | Rename ambiguous 'New' task button to 'Add Lead' | Sales - Tasks / Leads | Low | To Do

## Improvements Summary
ID | Improvement | Page / Module | Priority
TASK-003 | Plus-addressing (email alias) test accounts cause password-reset confusion | Auth / Password Reset, Onboarding | Medium
TASK-006 | API errors are not surfaced to the user with useful detail | Global / Error Handling | High
TASK-010 | Skills/Tools fields need multi-select or autocomplete instead of free typing | Talent Profile Form | Medium
TASK-013 | Convert Computer/OS field into a dropdown with Windows/Mac/Linux options | Talent Profile Form | Low
TASK-014 | Profile form fields should all be optional to allow partial save | Talent Profile Form | High
TASK-020 | Move Workspace Photo out of Documents dropdown into Personal/Contact section | Talent Profile Form | Medium
TASK-030 | Show the actual Account Manager's name instead of a generic label | Client Dashboard | Medium
TASK-033 | Differentiate 'Message' vs 'Project' as distinct structured conversation types | Messaging / Communication | High
TASK-039 | Replace default Stripe-branded 'Add Payment Method' page with custom-branded page | Finance / Billing | Medium
TASK-044 | Split Admin Users list by role (Admin / Client / Sales / Talent) | Admin - Users | High
TASK-046 | Rename Admin 'Projects' (triage) section for clarity | Admin - Projects | Low
TASK-052 | Merge Kanban/Task board view into the Leads table instead of a separate disconnected view | Sales - Leads / Pipeline | Medium
TASK-055 | Design a clearer, more guided workflow for creating a sales proposal/pricing | Sales - Proposals | High
TASK-061 | Remove/repurpose 'New Lead Assigned' notification given self-managed leads model | Sales - Notifications | Low

## New Features
ID | Feature | Page / Module | Priority
TASK-007 | No onboarding/instructions after accepting a Talent (VA) invite | Talent Portal / Onboarding | High
TASK-016 | Block access to other app sections until required profile section is complete | Talent Portal | Medium
TASK-017 | Add file type/size and duration limits for intro video upload | Talent Profile Form | Medium
TASK-018 | Allow recording the intro video directly on the Verity site | Talent Profile Form | Low
TASK-021 | Add a required profile headshot photo visible to clients | Talent Profile Form | Medium
TASK-022 | Add 'About Verity' (mission/vision) content to the Talent portal | Talent Portal | Low
TASK-023 | Build native time-tracking app with screenshots and activity monitoring | Time Tracker | High
TASK-024 | Add AI-based detection of mouse-jiggler / suspicious activity in time tracker | Time Tracker | Low
TASK-025 | Add mandatory 'Rules of Conduct' acknowledgment during onboarding | Onboarding (Talent) | High
TASK-026 | Add a 'Projects' section to the Talent (VA) portal | Talent Portal | Medium
TASK-029 | Client dashboard needs an explanation of what an 'Account Manager' is | Client Dashboard | Medium
TASK-031 | Build ability to assign an Account Manager to a client | Admin | Critical
TASK-040 | Define Account Manager workflow for handling disputed invoices | Finance / Billing | Medium
TASK-041 | Require client company info and agreements before granting full platform access | Client Onboarding | Medium
TASK-047 | Build VA directory with filtering and direct-message capability for assignment | Admin - Projects / Talent | High
TASK-048 | Build workflow to link/assign a VA to a client's project | Admin - Projects | Critical
TASK-059 | Add optional 'Sales Card' bio/profile page for digital business cards | Sales - Profile | Low
TASK-060 | Add default email signature template for sales reps | Sales - Settings | Low
TASK-064 | Add a site-wide Feedback button/section | Global | Medium

## UI-UX Suggestions
ID | Suggestion | Location | Component
TASK-003 | Plus-addressing (email alias) test accounts cause password-reset confusion | Auth / Password Reset, Onboarding | Login / Password Reset Form
TASK-008 | Yes/No profile fields should be toggle switches, not free text | Talent Profile Form | Form Field (Yes/No questions)
TASK-034 | Move the 'Message' button to a persistent floating button (bottom-right) on every page | Global Navigation | Message Button
TASK-035 | Add a visual badge/indicator distinguishing which chat is with a client vs. internal | Messaging / Communication | Chat Thread Header / Badge
TASK-043 | Clarify/rename the Admin 'Team' page (individuals vs. departments) and consider card view | Admin - Team | Team Page / List View
TASK-051 | Add sortable 'Date' column to Leads/Pipeline table | Sales - Leads / Pipeline | Leads Table
TASK-054 | Fix unstyled/ugly scrollbar on the Leads/Pipeline view | Sales - Leads / Pipeline | Scrollbar Styling

## Technical Tasks
ID | Task | Area | Dependencies
TASK-045 | Prevent accidental role changes when editing a user account | Admin - Users | RBAC system (mentioned as a future refinement)
TASK-049 | Decide real-time messaging approach: WebSocket/SSE vs. periodic polling | Messaging / Communication | Chat/messaging system

## Documentation Tasks
ID | Documentation | Owner (if mentioned)
TASK-015 | Clarify and document the 'freeze on submit' behavior for locked profile sections | Unknown
TASK-058 | Confirm document/knowledge-base folder categories are already dynamic (not hardcoded) | Unknown
TASK-065 | Publish a changelog with each production deploy | Unknown
TASK-068 | Complete sales user-story documentation based on current (not idealized) workflows | Unknown

## Research Tasks
ID | Research Topic | Reason
TASK-032 | Design auto-assignment logic for Account Manager based on workload rotation | Team discussed ideas for automatically distributing account-manager assignments (e.g., least number of accounts, role-ba
TASK-042 | Investigate automated (cron/AI) checks instead of manual-only compliance notifications | Team wondered whether compliance-related checks should be automated (scheduled job) rather than only firing as they happ
TASK-067 | Investigate AI coding assistant (Claude) slowness during development | A developer reported the AI coding assistant felt slower than usual, especially compared to how it performs on the landi

## Open Questions
ID | Question | Raised By
TASK-011 | Clarify delimiter/UX pattern for multi-value list fields (comma vs. add button) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable)
TASK-019 | Government ID upload feels intrusive to some VAs (needs review) | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable)
TASK-071 | Clarify distinction between 'Event' and 'Project' concepts in Admin/CRM | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable)
TASK-072 | Define the purpose and structure of the 'Engagements' section | Unknown (transcript diarization labels all speakers as a single name; individual speakers not distinguishable)

## Decisions Made
ID | Decision | Reason
TASK-012 | Remove 'Internet Provider' field; keep upload/download speed test fields | Team decided the ISP name itself is not useful information for (overseas) clients, but connection speed is.
TASK-027 | Restrict VA-client communication to the in-platform chat system only | Team decided VAs should communicate with their assigned client only through the platform's built-in chat, not other channels.
TASK-038 | Switch client billing cycle from monthly to weekly (paid in advance) | Team debated monthly vs weekly billing; decided weekly (charged every Monday, similar to Upwork) is safer for cash flow and dispute risk while the company is sm
TASK-050 | Scope sales leads to the owning sales rep by default (no cross-rep visibility) | Leads are currently shown under an 'All' filter across sales reps; team decided each rep should see only their own leads by default, with admins seeing everyone
TASK-056 | Introduce a dedicated 'Project Manager' role, separate from Admin | Team decided project management responsibilities (communicating with sales, client, and assigned VA) should be a distinct role from full Admin, with access limi
TASK-057 | Decide VA-client contact channel: allow external channels (e.g., WhatsApp) for sales with note-logging | Team decided sales reps may continue using external channels like WhatsApp with clients for convenience, but should log notes on the lead record, while in-platf
TASK-062 | Keep 'Follow-up due' reminder and 'Monday summary' notification features as-is | Team reviewed existing notification ideas and explicitly approved keeping follow-up reminders and a Monday summary digest.
TASK-063 | Keep sales goals/targets tracker feature as-is | Team approved the existing goals/targets feature (e.g., number of clients or hours) for motivating and tracking sales reps.
TASK-073 | VAs should log their own project milestones/work as a 'proof of work' journal | For clients who use their own external project-management tools, the team decided VAs should still independently track milestones/work in Verity as a protective

## Duplicate Requests
Request | Number of Mentions | Related Task IDs
Post-verification redirect points to localhost instead of production URL | 2 | TASK-001
Plus-addressing (email alias) test accounts cause password-reset confusion | 3 | TASK-003
Yes/No profile fields should be toggle switches, not free text | 2 | TASK-008
Move the 'Message' button to a persistent floating button (bottom-right) on every page | 2 | TASK-034